## Function Points
FUNCTION POINT CALCULATION |  |  |  |  | Language | English |  | Adjusted FP |  | 77.22
No. |  | VAF | Weight: 0 (low) ~ 5 (high)
1 | Data communications |  | 4
2 | Distributed data processing |  | 3
3 | Performance |  | 4
4 | Heavily used configuration |  | 3 |  | FP: | Function Point
5 | Transaction rate |  | 4 |  | VAF: | Value Added Factor |  | Complexity Adjustment Factor
6 | On-Line data entry |  | 5 |  | DET: | Data Element Type
7 | End-user efficiency |  | 4 |  | RET: | Record Element Type
8 | On-Line update |  | 4 |  | FTR: | File Types Referenced
9 | Complex processing |  | 3 |  | ILF: | Internal Logical Files
10 | Reusability |  | 4 |  | EIF: | External Interface Files
11 | Installation ease |  | 4 |  | EI: | External Inputs
12 | Operational ease |  | 4 |  | EO: | External Outputs
13 | Multiple sites |  | 2 |  | EQ: | External Inquiry
14 | Facilitate change |  | 4
|  | VAF | 52
[8 empty] | Unadjusted FP |  | 66
[8 empty] | Adjusted FP |  | 77.22
No. | Module | Function Name | Description | Type | DET | RET / FTR | Complexity | FP | Adjust % | FP adjusted | Remarks
1 | welcome page | start |  | EQ | 1 | 1 | Low | 3 |  | 3
2 | log in/sign up | log in |  | EI | 2 | 1 | Low | 6 |  | 6
5 | map view | wallet |  | EQ | 4 | 2 | Low | 3 |  | 3
6 | map view | recenter |  | EQ | 1 | 1 | Low | 3 |  | 3
7 | map view | pin | shows business summary | EQ | 1 | 1 | Low | 3 |  | 3
8 | map view | business name |  | EQ | 1 | 5 | Average | 4 |  | 4
9 | wallet view | sign out |  | EI | 1 | 1 | Low | 3 |  | 3
10 | wallet view | back |  | EI | 1 | 1 | Low | 3 |  | 3
11 | busniess view | back |  | EI | 1 | 1 | Low | 3 |  | 3
12 | busniess view | review |  | EI | 1 | 1 | Low | 3 |  | 3
15 | review | submit | text input+score | EO | 3 | 2 | Low | 4 |  | 4
16 | review | back |  | EI | 1 | 1 | Low | 3 |  | 3
17 | review fail | ok |  | EI | 1 | 1 | Low | 3 |  | 3
18 | review submitted | ok |  | EI | 1 | 1 | Low | 3 |  | 3
19 | business owner view | sign out |  | EI | 1 | 1 | Low | 3 |  | 3
20 | business owner view | open camera |  | EI | 1 | 1 | Low | 3 |  | 3
21 | camera | scan qr code |  | EQ | 1 | 1 | Low | 3 |  | 3
22 | camera | back |  | EI | 1 | 1 | Low | 3 |  | 3
23 | redeem view | back |  | EI | 1 | 1 | Low | 3 |  | 3
24 | redeem view | confirm | select points and confirm | EO | 2 | 1 | Low | 4 |  | 4

## table
Data Functionalities |  |  |  |  | Counting |  |  |  |  | Localization
| ILF / ELF |  | DET |  |  | FP |  | Complexity |  |  |  | language
| RET | 1 | 20 | 51 |  | Type | Low | Average | High |  | Label | English
| 1 | Low | Low | Average |  | ILF | 7 | 10 | 15
| 2 | Low | Average | High |  | EIF | 5 | 7 | 10 |  | module | Module
| 6 | Average | High | High |  | EI | 3 | 4 | 6 |  | functionname | Function Name
[6 empty] | EO | 4 | 5 | 7 |  | functiondesc | Description
Transactional FP | [5 empty] | EQ | 3 | 4 | 6 |  | type | Type
| EI |  | DET | [7 empty] | complexity | Complexity
| FTR | 1 | 5 | 16 | [6 empty] | adjustpercent | Adjust %
| 1 | Low | Low | Average | [6 empty] | fpadjusted | FP adjusted
| 2 | Low | Average | High | [6 empty] | remarks | Remarks
| 3 | Average | High | High | [6 empty] | language | Language
[11 empty] | adjustedfp | Adjusted FP
| EO / EQ |  | DET | [7 empty] | unadjustedfp | Unadjusted FP
| FTR | 1 | 6 | 20
| 1 | Low | Low | Average | [6 empty] | vaf-weight | Weight: 0 (low) ~ 5 (high)
| 2 | Low | Average | High | [6 empty] | vaf01 | Data communications
| 4 | Average | High | High | [6 empty] | vaf02 | Distributed data processing
[11 empty] | vaf03 | Performance
[11 empty] | vaf04 | Heavily used configuration
[11 empty] | vaf05 | Transaction rate
[11 empty] | vaf06 | On-Line data entry
[11 empty] | vaf07 | End-user efficiency
[11 empty] | vaf08 | On-Line update
[11 empty] | vaf09 | Complex processing
[11 empty] | vaf10 | Reusability
[11 empty] | vaf11 | Installation ease
[11 empty] | vaf12 | Operational ease
[11 empty] | vaf13 | Multiple sites
[11 empty] | vaf14 | Facilitate change

## CoCoMo II
http://softwarecost.org/tools/COCOMO/